## WBS
Work Breakdown Structure (WBS)
＃ | Tasks | Owner | Status | Start Date | End Date | Duration (days) | Progress | January | [11 empty] | February
[8 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
[8 empty] | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
1 | Project Initiation (Week 1) |  |  | 2026-01-20 | 2026-01-26 | 7
1.1 | Form project group
| Form group | All | Done | 2026-01-20 | 2026-01-20 | 1 | 100% | bar: January 20 Tue
| Take a group photo | All | Done | 2026-01-20 | 2026-01-29 | 10 | 100% | bar: January 20 Tue to January 29 Thu
1.2 | Set up development environment
| Request GitHub repository to Alex | Yinuo | Done | 2026-01-20 | 2026-01-25 | 6 | 100% | bar: January 20 Tue to January 25 Sun
| Update member lists on GitHub | All | In Progress | 2026-01-20 | 2026-01-26 | 7 | 60% | bar: January 20 Tue to January 26 Mon
| Update group photo on GitHub | Shiho | In Progress | 2026-01-20 | 2026-01-26 | 7 | 0% | bar: January 20 Tue to January 26 Mon
1.3 | Game research
| Analyse existing games | All | Done | 2026-01-20 | 2026-01-26 | 7 | 100% | bar: January 20 Tue to January 26 Mon
1.4 | Idea generation
| Brainstorm game concepts | All | Done | 2026-01-20 | 2026-01-26 | 7 | 100% | bar: January 20 Tue to January 26 Mon
| Produce two candidate game ideas | All | Done | 2026-01-20 | 2026-01-26 | 7 | 100% | bar: January 20 Tue to January 26 Mon
2 | Requirements & Planning (Weeks 2–4) |  |  | 2026-01-27 | 2026-02-16 | 21
2.1 | p5.js practice (painting tool)
| Choose a Kanban board tool | Yuqi | In Progress | 2026-01-27 | 2026-02-02 | 7 | 0% | bar: January 27 Tue to February 2 Mon
| Setting up a Kanban board tool |  | Open | 2026-01-27 | 2026-02-02 | 7 | 0% | bar: January 27 Tue to February 2 Mon
2.2 | p5.js practice (painting tool)
| Decide which tool to submit | All | Done | 2026-01-27 | 2026-01-30 | 4 | 100% | bar: January 27 Tue to January 30 Fri
| Upload the code to GitHub | Yinuo | In Progress | 2026-01-27 | 2026-02-02 | 7 | 0% | bar: January 27 Tue to February 2 Mon
2.3 | Description of the two candidate games
| Add a description of Pocket Tanks | Nikolay | In Progress | 2026-01-27 | 2026-02-02 | 7 | 0% | bar: January 27 Tue to February 2 Mon
| Add a description of Cutthroat Island | Yinuo | In Progress | 2026-01-27 | 2026-02-02 | 7 | 0% | bar: January 27 Tue to February 2 Mon
2.4 | Prototyping
| Create paper prototype | All | Open | 2026-02-03 | 2026-02-09 | 7 | 0% | bar: February 3 Tue to February 9 Mon
| Take a video of prototype introduction | All | Open | 2026-02-03 | 2026-02-09 | 7 | 0% | bar: February 3 Tue to February 9 Mon
| Digital wireframes | All | Open | 2026-02-03 | 2026-02-09 | 7 | 0% | bar: February 3 Tue to February 9 Mon
2.5 | Game requirements
| Core gameplay loop | All | Open | TBD | 2026-02-16
| Win/lose conditions | All | Open | TBD | 2026-02-16
| Scoring and progression | All | Open | TBD | 2026-02-16
2.6 | Requirements documentation
| Functional requirements | All | Open | TBD | 2026-02-16
| Non-functional requirements | All | Open | TBD | 2026-02-16
| Ethical considerations and constraints | All | Open | TBD | 2026-02-16

## Deliverables
Project: Agile Game Development
Methodology: Agile / Iterative (Scrum-like)
Deliverables:
・Game source code (GitHub)
・Playable demo (e.g. GitHub Pages)
・Demo / gameplay video
・Project report
・Group viva preparation

## Lists
Member | Status
All | Open
Hsinman | In Progress
Nikolay | Done
Shiho
Yinuo
Yuqi
Yuxin